## sprint_two(Sheet1)
Task | Associated Story | Assignee | Difficulty | Status
Comprehensive read me |  | Ashley | 5 | done
Progress Report One |  | Ashley | 9 | Done
Design Dashboard | As a shop owner I would like a dashboard to help navigate my shop | Ashley | 7 | Done
Code in Linked functionality | As a shop owner I would like a dashboard to help navigate my shop | Ben C | 8 | In progress and moved to next sprint
Creating testing | As a shop owner I would like a dashboard to help navigate my shop | UNASSIGNED |  | Moved to new sprint
Create User profile Page functionality | As a user with an account I should have a user profile page | Spencer | 7 | In progress and moved to next sprint
Design profile page | As a user with an account I should have a user profile page | Braden | 5 | Done
create HTML/css for store dashboard | As a user with an account I should have a user profile page | Spencer |  | In progress and moved to next sprint
create testing | As a user with an account I should have a user profile page | UNASSIGNED |  | Moved to new sprint
Design display for items | As a store owner I want to display items and categories to customers | Ashley | 8 | Done
Design display for categories | As a store owner I want to display items and categories to customers | Ashley | 8 | Done
Code backend for getting categories and items | As a store owner I want to display items and categories to customers | Adam | 5 | in progress and moved to next sprint
Create front end code for displaying items | As a store owner I want to display items and categories to customers | Ben D | 8 | Done
Creating testing | As a store owner I want to display items and categories to customers |  | 4 | Moved to new sprint
Design UI for adding and removing items from shopping cart | As a customer, I want to be able to add/remove items from my shopping cart | Ashley | 5 | Done
Create table for shopping cart items | As a customer, I want to be able to add/remove items from my shopping cart | Adam | 7 | Done
Code adding and removing function | As a customer, I want to be able to add/remove items from my shopping cart | Ben C | 7 | In progress and moved to next sprint
Create testing for adding and removing | As a customer, I want to be able to add/remove items from my shopping cart |  |  | Moved to new sprint
Code customer view page of landing page |  | Braden | 7 | Done