## sprint_four(Sheet1)
Task | Associated Story | Assignee | Difficulty | Status
progress report two |  | Ashley | 8 | Done
Create UI to save data | As a customer I want to be able to save my delivery and payment information to an account | Spencer | 6 | to do
add delivery coloumn | As a customer I want to be able to save my delivery and payment information to an account | Ben C | 3 | Done
Add payment column | As a customer I want to be able to save my delivery and payment information to an account | Spencer | 3 | to do
Add securtiy Measures | As a customer I want to be able to save my delivery and payment information to an account | Ben D | 7 | to do, moving into next sprint
Create services to manage this information using encryption | As a customer I want to be able to save my delivery and payment information to an account | Ben D | 7 | to do. moving to next sprint
Create Testing for saving info | As a customer I want to be able to save my delivery and payment information to an account | Steven | 5 | to do
Create UI for buying items | As a customer, I want to be able to purchase all the items in my shopping cart at once, using the same delivery and payment information | Braden | 6 | Done
code payment processing | As a customer, I want to be able to purchase all the items in my shopping cart at once, using the same delivery and payment information | Ben D | 8 | in progress and moving into next sprint
code purchasing | As a customer, I want to be able to purchase all the items in my shopping cart at once, using the same delivery and payment information | Ben C | 8 | in progress and moving into next sprint
Create Testing | As a customer, I want to be able to purchase all the items in my shopping cart at once, using the same delivery and payment information | Steven | 7 | to do
Create UI for slecting variation | As a store owner, I want to be able to display if there are variations of a product (sizing, colour, etc) | Adam | 6 | in progress and moving into next sprint
Code varistions function | As a store owner, I want to be able to display if there are variations of a product (sizing, colour, etc) | Adam | 8 | in progress and moving into next sprint
Code API calls to database | As a store owner, I want to be able to display if there are variations of a product (sizing, colour, etc) | Adam | 9 | Done
Create testing | As a store owner, I want to be able to display if there are variations of a product (sizing, colour, etc) | Steven | 3 | to do
test mobile web verion | As a customer, I want to be able to view stores on various different devices | Steven | 4 | to do
create mobile web version | As a customer, I want to be able to view stores on various different devices | Steven | 6 | to do