## sprint_three(Sheet1)
Task | Associated Story | Assignee | Difficulty | Status
Design Dashboard | As a shop owner I would like a dashboard to help navigate my shop | Ashley | 7 | Done
Creating HTML/CSS for shop dashboard | As a shop owner I would like a dashboard to help navigate my shop | Spencer | 8 | Done
Code linked in functionality | As a shop owner I would like a dashboard to help navigate my shop | Ben C | 8 | In progress and working on in next sprint
Create testing | As a shop owner I would like a dashboard to help navigate my shop | UNASSIGNED | 6 | To do
Set Up URL making | As a store owner, I want to be able to share my store with URLs that specify a specific focus of my store, store/category/item | Ben C | 3 | In progress and working on in next sprint
Create testing for URL | As a store owner, I want to be able to share my store with URLs that specify a specific focus of my store, store/category/item | UNASSIGNED | 8 | to-do
Create table in database for themes | As a store owner, I want to be able to create the theme and add logos/branding to my store | Ben C | 4 | Done
Create table in database for logos | As a store owner, I want to be able to create the theme and add logos/branding to my store | Ben C | 5 | Done
Code Theme selecting functionality | As a store owner, I want to be able to create the theme and add logos/branding to my store | Ben D | 9 | Done
Code logo selecting functionality | As a store owner, I want to be able to create the theme and add logos/branding to my store | Ben D | 2 | Done
Design theme selector UI | As a store owner, I want to be able to create the theme and add logos/branding to my store | Ashley | 7 | Done
Design preset themes | As a store owner, I want to be able to create the theme and add logos/branding to my store | Ashley | 6 | Done
Design UI for adding logos | As a store owner, I want to be able to create the theme and add logos/branding to my store | Ashley | 4 | Done
Create testing for theme and logo selecting | As a store owner, I want to be able to create the theme and add logos/branding to my store | UNASSIGNED | 7 | to do
Design Ui for adding photos | As a store owner, I want to be upload photos of my product to a listing | Ashley | 3 | Done
edit store item display UI to display photos and categories | As a store owner, I want to be upload photos of my product to a listing | Ashley | 9 | Done
Code retrivial of photos for display | As a store owner, I want to be upload photos of my product to a listing | Adam | 8 | Done
Code adding of photos | As a store owner, I want to be upload photos of my product to a listing | Adam | 5 | Done
Create database table to store photos | As a store owner, I want to be upload photos of my product to a listing | Ben C | 4 | Done
Testing displaying images | As a store owner, I want to be upload photos of my product to a listing | UNASSIGNED |  | To-do
Create Testing of adding photos | As a store owner, I want to be upload photos of my product to a listing | UNASSIGNED |  | To-do
Create backend code for editing stocks | As a store owner, I want to update the stock of my products, whether it be in stock or out of stock | Ben D | 3 | Done
create UI for editing stock | As a store owner, I want to update the stock of my products, whether it be in stock or out of stock | Ben D | 3 | Done
test stock function | As a store owner, I want to update the stock of my products, whether it be in stock or out of stock | UNASSIGNED | 1 | To-Do