## Sprint_Five(Sheet1)
Task | Associated Story | Assignee | Difficulty | Status
User Requirements documentation |  | Ashley Bishop | 7 | Done
Edit item listing design to account for variations of a product |  | Ashley Bishop | 6 | Done
Design social media integration pages |  | Ashley Bishop | 6 | Done
Update existing APIs to handle requests from both authenticated and guest users, ensuring proper data validation and processing. | As a customer I want to be able to use the store without having to login to an account | Ben Combe | 7 | Done
Implement session handling to maintain guest user state during their visit, including cart persistence and temporary data storage. | As a customer I want to be able to use the store without having to login to an account | Ben Combe | 8 | Done
Ensure that order data from guest users is stored securely and can be retrieved if the user decides to create an account later or needs support. | As a customer I want to be able to use the store without having to login to an account | Ben Combe | 8 | Did not get done
Develop the backend and frontend components that allow users to make purchases without creating an account, including collecting necessary information (e.g., shipping address, payment details). | As a customer I want to be able to use the store without having to login to an account | Ben Combe | 7 | Did not get done
Conduct comprehensive testing, including unit tests, integration tests, and user acceptance testing, to ensure that guest functionality works seamlessly and securely. | As a customer I want to be able to use the store without having to login to an account | UNASSIGNED |  | Did not get done
UI for seeing all items in shopping cart | As a customer, I want to be able to see all the items in my shopping cart | Ben Combe | 7 | Done in previous sprint
Code retrieving full list of cart items and display | As a customer, I want to be able to see all the items in my shopping cart | Ben Combe | 7 | Done in previous sprint
Create Testing | As a customer, I want to be able to see all the items in my shopping cart | Steven Putter | 6
Edit store item display UI to display photos and categories | As a store owner, I want to upload photos of my product to a listing | Ashley Bishop | 9 | Done in previous sprint
Code retrieval of photos for display | As a store owner, I want to upload photos of my product to a listing | Adam Shariff | 8 | Done in previous sprint
Design UI for adding photos | As a store owner, I want to upload photos of my product to a listing | Ashley Bishop | 3 | Done in previous sprint
Code adding of photos | As a store owner, I want to upload photos of my product to a listing | Adam Shariff | 5 | Done in previous sprint
Create database table to store photos | As a store owner, I want to upload photos of my product to a listing | Ben Combe | 4 | Done in previous sprint
Testing of displaying images | As a store owner, I want to upload photos of my product to a listing | UNASSIGNED | 5
Create testing of adding photos | As a store owner, I want to upload photos of my product to a listing | UNASSIGNED | 4
Design theme selector | As a store owner, I want to be able to create the theme and add logos/branding to my store | Ashley Bishop | 7 | Done in previous sprint
Design preset themes | As a store owner, I want to be able to create the theme and add logos/branding to my store | Ashley Bishop | 6 | Done in previous sprint
Design UI for adding photos | As a store owner, I want to be able to create the theme and add logos/branding to my store | Ashley Bishop | 4 | Done in previous sprint
code logo selecting funcationality | As a store owner, I want to be able to create the theme and add logos/branding to my store | Ben Dehooge | 2 | Done in previous sprint
Code theme selecting functionality | As a store owner, I want to be able to create the theme and add logos/branding to my store | Ben Dehooge | 9 | Done in previous sprint
Create table in database for themes | As a store owner, I want to be able to create the theme and add logos/branding to my store | Ben Combe | 4 | Done in previous sprint
Create table for logos in database | As a store owner, I want to be able to create the theme and add logos/branding to my store | Ben Combe | 5 | Done in previous sprint
Create testing for theme slection and logo adding | As a store owner, I want to be able to create the theme and add logos/branding to my store | UNASSIGNED
Set up URL making | as a store owner, I want to be able to share my store with URLs that specify focus of my store, store/ category/ item | Ben Combe | 3 | Done
Create testing for URLs | as a store owner, I want to be able to share my store with URLs that specify focus of my store, store/ category/ item | UNASSIGNED | 8
Design dashboard | As a store owner I would like a dashboard to help navigate my store | Ashley Bishop | 7 | Done in previous sprint
Creating HTML/CSS for shop dashboard | As a store owner I would like a dashboard to help navigate my store | Spencer Ing | 8 | Done in previous sprint
Code linked in functionlity | As a store owner I would like a dashboard to help navigate my store | Ben Combe | 8 | Done
Create Testing | As a store owner I would like a dashboard to help navigate my store | UNASSIGNED
Ensure that only authorized store owners can access the insights dashboard, implementing role based access controls as needed | As a store owner, I want to be able to view insights on the store( trends, popularity, etc..) | Ben Combe | 8 | In progress
Integrate the frontend with backend APIs and implement data visualization componenets ( charts, graphs, tbales) | As a store owner, I want to be able to view insights on the store( trends, popularity, etc..) | Adam Shariff | 7 | Done
Develop secure API endpoints that deliver the aggregated insights data to the front end | As a store owner, I want to be able to view insights on the store( trends, popularity, etc..) | Adam Shariff | 7 | Done
Create backend services to aggreagate and process data for various insights ensuring data accuracy and consistency. | As a store owner, I want to be able to view insights on the store( trends, popularity, etc..) | Adam Shariff | 7 | Done
Update or optimize the database schema to efficiently store and retrieve data needed for insights , including indexing and normalization as necessary | As a store owner, I want to be able to view insights on the store( trends, popularity, etc..) | Spencer Ing | 7 | Did not get done
Identify all data sources required for generating insights ( e.g, sales data, inventory levels, customer data) and map how they will be integrated | As a store owner, I want to be able to view insights on the store( trends, popularity, etc..) | Adam Shariff | 6 | Done
Add reviews table to the database to store all reviews by store-name/product id | As a customer, I wanr ro be able to leave reviews and ratings on specific products and be able to view users reviews | Ben Dehooge | 2 | Done
Design UI for displaying and creating reviews | As a customer, I wanr ro be able to leave reviews and ratings on specific products and be able to view users reviews | Ashley Bishop | 8 | Done in previous sprint
Create a review service/contoller in frontend and backend to fetch revies for a product and calculate average rating, etc. | As a customer, I wanr ro be able to leave reviews and ratings on specific products and be able to view users reviews | Ben Dehooge | 8 | Done
Create testing | As a customer, I wanr ro be able to leave reviews and ratings on specific products and be able to view users reviews | UNASSIGNED | 3
Test that users can not access other shops shopping carts | As a customer, I want to have different carts for whichever store I am currently shopping in | Spencer Ing | 4 | Did not get done
Create front end assets for banners | As a store owner, I would like scrolling banners when previewing my products | Braden Lucas | 7 | moved back into backlog and decided we did not need this
Implement image storage for banners on backend | As a store owner, I would like scrolling banners when previewing my products | UNASSIGNED | 6