## Sprint_Six(Sheet1)
Task | Associated story | Assignee | Difficulty | Status
Final Report |  | Ashley Bishop | 9 | Done
Sprint Log |  | Ashley Bishop | 6 | Done
User Manual |  | Ashley Bishop | 7 | Done
Add start and end times of product availability to item class | As a store owner, I want to have specfic timed release dates for my product(s) and when they are deleted | Ben DeHooge | 6 | Done
Add optional product release date input into item creation form | As a store owner, I want to have specfic timed release dates for my product(s) and when they are deleted | Ben DeHooge | 4 | Done
add field in database for start and end time | As a store owner, I want to have specfic timed release dates for my product(s) and when they are deleted | Ben DeHooge | 3 | Done
create testing | As a store owner, I want to have specfic timed release dates for my product(s) and when they are deleted | UNASSIGNED | 4
UI for adding social media | As a store owner, I want to have social media integrations and be able to send messages about my products | UNASSIGNED | 6 | unfinished due to time contraints
UI for creating a post | As a store owner, I want to have social media integrations and be able to send messages about my products | UNASSIGNED | 7 | unfinished due to time contraints
Coding Meta AI connection | As a store owner, I want to have social media integrations and be able to send messages about my products | UNASSIGNED | 5 | unfinished due to time contraints
Coding message sending functionality | As a store owner, I want to have social media integrations and be able to send messages about my products | UNASSIGNED | 3 | unfinished due to time contraints
create testing | As a store owner, I want to have social media integrations and be able to send messages about my products | UNASSIGNED | 7
create testing for account history | As a customer, I want to be able to create a wish list, or a favorites page of items and stores |  | 6 | unfinished due to time contraints
create UI for customer login | As a customer, I want to be able to create a wish list, or a favorites page of items and stores | Ben Combe | 7 | Done
code customer login logic | As a customer, I want to be able to create a wish list, or a favorites page of items and stores | Ben Combe | 7 | Done
create payments tabe | As a customer, I want to be able to create a wish list, or a favorites page of items and stores | UNASSIGNED | 6 | unfinished due to time contraints
create testing for account login/setup | As a customer, I want to be able to create a wish list, or a favorites page of items and stores | UNASSIGNED | 6
Create testing for currency conversion | As a customer, I want to be able to view different currencies when checking out the item in my cart | UNASSIGNED | 2 | unfinished due to time contraints
implement currencies conversions on the backend | As a customer, I want to be able to view different currencies when checking out the item in my cart | UNASSIGNED | 4 | unfinished due to time contraints
implement front end assests for switching currencies | As a customer, I want to be able to view different currencies when checking out the item in my cart | UNASSIGNED | 6 | unfinished due to time contraints
Design and implement the user interface components to display reccomended items on the product detail page, ensuring they are visually appealing and non-intrusive | As a store owner, I want reccomended items from my store to appear when viewing an item in my store | Braden Lucas | 7 | Done
Conduct unit testing, integration testing and A/B testing to ensure the recommendations are accurate, relevant and do not negatively impact page performance | As a store owner, I want reccomended items from my store to appear when viewing an item in my store | UNASSIGNED | 8 | unfinished due to time contraints
Allow store owners to customize recommendation settings, such as the number of recommendations, types of recommendation and the placemen on the page | As a store owner, I want reccomended items from my store to appear when viewing an item in my store | UNASSIGNED | 7 | unfinished due to time contraints
Create secure and efficient API endpoints that deliver recommended items based on the current item being viewed | As a store owner, I want reccomended items from my store to appear when viewing an item in my store | UNASSIGNED | 7 | unfinished due to time contraints
Implement the chosen reccomendation algorithms possibly leveraging machine earning libraries or third party services, to generate relevent item suggestions | As a store owner, I want reccomended items from my store to appear when viewing an item in my store | UNASSIGNED | 8 | unfinished due to time contraints
Identify and prepare the necessary data sources, such as purchse history, product meta data and user interactions, ensuring data quality and consistency | As a store owner, I want reccomended items from my store to appear when viewing an item in my store | UNASSIGNED | 7 | unfinished due to time contraints
Decide on the reccomendation algorithms to be used (e.g., collaborative filtering, content-based filtering, hybrid methods) and outline the logic for item selection | As a store owner, I want reccomended items from my store to appear when viewing an item in my store | UNASSIGNED | 7 | unfinished due to time contraints
Create receipt design | As a cusomter, I want to recieve a receipt after a purchase | Ashley Bishop | 5 | Done
Code receipt sending function | As a cusomter, I want to recieve a receipt after a purchase | UNASSIGNED | 6 | unfinished due to time contraints
create testing | As a cusomter, I want to recieve a receipt after a purchase | UNASSIGNED | 6 | unfinished due to time contraints
|  | UNASSIGNED |  | unfinished due to time contraints
Create UI for deletion | As a store owner, I want to be able to delete my store | UNASSIGNED | 6 | unfinished due to time contraints
Code deletion functionality | As a store owner, I want to be able to delete my store | UNASSIGNED | 7 | unfinished due to time contraints
create testing | As a store owner, I want to be able to delete my store | UNASSIGNED | 5 | unfinished due to time contraints